## Slide 1
Global ERA5 Data Preparation for Chronos-2 LAI Forecasting
1
WEEKLY RESEARCH UPDATE
▪ This week's focus: preparing ERA5 global meteorological data to extend our Chronos-2 LAI forecasting framework beyond the continental U.S.
▪ Covered here: why ERA5, how it maps onto our existing 7-variable pipeline, the global non-U.S. pixel selection, current download progress, and next steps.
TAKEAWAY
Pipeline and experiment design are essentially ready; ERA5 data download is the one remaining dependency before running the global experiment.

## Slide 2
MOTIVATION
Extending Beyond gridMET's U.S.-Only Coverage
2
▪ Every Chronos-2 LAI experiment so far has used gridMET, a daily ~4km meteorological product that only covers the continental United States.
▪ Professor Wang suggested using ERA5 instead, so we can test whether zero-shot Chronos-2 generalizes to vegetation and climate regimes well outside the U.S.
▪ ERA5 (ECMWF's 5th-generation reanalysis) provides the same kind of variables at a consistent 0.25° resolution anywhere on Earth, which lets us reuse one common data source globally.
▪ Research question: how well does zero-shot Chronos-2 forecast LAI across diverse global vegetation and climate regimes when ERA5 supplies the meteorological input?
TAKEAWAY
ERA5 is the key that unlocks testing our framework anywhere in the world, not just the U.S.

## Slide 3
DATA SOURCE & VARIABLE MAPPING
Mapping ERA5 to Our Existing 7 Climate Variables
3
Product:
derived-era5-single-levels-daily-statistics
(Copernicus Climate Data Store) — global 0.25° reanalysis with server-side daily aggregation, so we never download raw hourly data.
Pipeline variable | ERA5 source | How it's obtained
tmmx (max temp) | 2m_temperature | direct (daily maximum)
tmmn (min temp) | 2m_temperature | direct (daily minimum)
pr (precipitation) | total_precipitation | direct (daily sum, m → mm)
srad (solar radiation) | surface_solar_radiation_downwards | direct (daily mean, J/m² → W/m²)
vpd (vapor pressure deficit) | 2m_temperature + 2m_dewpoint_temperature | derived, FAO-56 Penman-Monteith formula
sph (specific humidity) | 2m_dewpoint_temperature + surface_pressure | derived
vs (wind speed) | 10m u- and v-wind components | magnitude of daily-mean vector
TAKEAWAY
Every mapping and unit conversion was verified against real downloaded values first, not assumed from documentation.

## Slide 4
DATA PROCESSING
Plugging ERA5 into the Existing Pipeline, Unchanged
4
▪ ERA5 daily values are aligned to each LAI 8-day composite window using the exact same windowed-mean convention our gridMET pipeline already uses — not a naive calendar-week average.
▪ The core Chronos-2 input-building and zero-shot prediction code required zero changes — only a new ERA5 data-preparation adapter was added.
▪ This keeps ERA5-based results directly comparable to our existing gridMET results, and keeps the design open to future meteorological sources (e.g., Earth System Model output).
TAKEAWAY
ERA5 is a drop-in replacement for gridMET at the input layer — the model and evaluation code are untouched.

## Slide 5
GLOBAL EXPERIMENT SETUP
45 Representative Non-U.S. Pixels Selected
5
▪ Selected from the global ESA CCI Plant Functional Type (PFT) product (300m, true global coverage) — not the CONUS-only copy used in prior experiments.
▪ Chosen by farthest-point sampling in PFT-composition space, combined with a minimum 800km geographic separation — not hand-picked or random similar sites.
▪ The continental U.S., Alaska, and Hawaii are explicitly excluded.
45
non-U.S. pixels
10
PFT classes represented
13
world regions covered
0.44–1.00
PFT purity range
Top regions: Siberia/Boreal Eurasia (9), Canada (5), East Asia (4), Amazon (3), Western Europe (3), East Africa/Sahel (2), Central/Southern Africa (2)
TAKEAWAY
Coverage spans forests, grasslands, and shrublands across every inhabited continent.

## Slide 6
CURRENT STATUS
ERA5 Download In Progress — Working Through CDS Constraints
6
▪ Currently validating the ERA5 pipeline on an existing CONUS pixel before scaling to the 45 global pixels, to catch any unit or alignment errors early.
▪ The Copernicus Climate Data Store (CDS) imposes two hard, undocumented limits found through direct testing: only one request in flight per account at a time, and a tight per-request size cap (effectively one variable, one year, per request).
▪ Per-request queue wait time varies widely (minutes to tens of minutes) and is controlled entirely by CDS, not by us.
▪ This week also included a multi-hour, account-wide CDS service outage — confirmed by testing unrelated requests and cross-checking the ECMWF community forum — independent of our pipeline.
▪ The download is fully resumable: every (variable, year, location) combination is cached individually, so no progress is ever lost across interruptions.
TAKEAWAY
The bottleneck is CDS's own queue and rate limits, not our pipeline — the resumable design keeps making steady progress regardless.

## Slide 7
STATUS SUMMARY
What's Done, What's Still Running
7
COMPLETED
▪ ERA5 variable mapping and unit conversions (verified empirically)
▪ ERA5-to-LAI temporal alignment logic
▪ Chronos-2 integration (reuses the existing pipeline unchanged)
▪ Global non-U.S. pixel selection (45 pixels)
STILL IN PROGRESS
▪ ERA5 download for the pipeline validation pixel
▪ Full 45-pixel global ERA5 download (not yet started)
▪ Global zero-shot Chronos-2 evaluation (blocked on the download above)
TAKEAWAY
Data preparation is essentially complete — the remaining work is waiting on CDS downloads, not new design or engineering.

## Slide 8
NEXT STEPS
From Data Preparation to Global Experiments
8
▪ Finish the ERA5 download for the validation pixel and compare zero-shot Chronos-2 results against the existing gridMET baseline.
▪ Once validated, launch the ERA5 download for the full 45-pixel global set.
▪ Run zero-shot Chronos-2 across all 45 pixels and analyze results by vegetation type, climate regime, and region.
▪ Compare global (ERA5) generalization performance against our existing U.S. (gridMET) results.
TAKEAWAY
Next week's goal: move from data preparation into running and analyzing the global Chronos-2 experiment itself.